DromGrader: USC Housing Mobile Application Project

(Part 1)

### ISE515 Engineering Project Management Professor Herag Haleblian

### Team 4

### Diya Shah, Guozheng Yang, Mihir Kavishwar, Rhythm Deo, Sami Andari

Table of Contents

## Part 1: Project Initiation & Planning

- Board of Directors/Project Sponsor meeting	3

- Project Charter	5

- Work Breakdown Structure (WBS)	13

- Resource Plan	19

- Project Organization	22

- Project Schedule	24

- Risk Plan	29

Part 1: Project Initiation & Planning

# Board of Directors/Project Sponsor meeting:

##### Meeting Recap: Board of Directors/Project Sponsor Meeting

Date: October 17, 2023, Time: 4:10 PM

##### Attendees:

Board of Directors:

  - Diya Shah

  - Guozheng Yang

  - Mihir Kavishwar

  - Rhythm Deo

  - Sami Andari

Project Sponsor:

  - Professor Herag Haleblian

##### Agenda:

  - Welcome and Introduction

  - Project Overview: Explanation and Purpose

  - Clarification on Scope of Project

    - Specific Technological Platforms

    - Security Measures

    - Data and Feature Inclusions

    - Success Metrics

  - Estimated Budget and Time Frame

  - Feedback Session: Inputs from Board Members

  - Closing Remarks

##### Meeting Summary:

The October 17, 2023, Board of Directors/Project Sponsor Meeting was conducted with a structured approach to address the upcoming project's scope and relevant details. Professor Herag Haleblian, our esteemed Project Sponsor, provided a comprehensive project overview, emphasizing its significance within our academic journey.

Key points of discussion included:

Technological Platforms: The board sought clarity on platform preferences, and Professor Herag affirmed the flexibility to select platforms that align with project objectives.

Security Measures: Queries regarding stringent security guidelines were answered with a reassurance of our autonomy in determining security measures.

Data and Features: Specific inclusions were discussed, with Professor Herag encouraging creativity and flexibility in our approach.

Budget and Time Frame: The meeting delved into estimated budget requirements and the establishment of a realistic timeline. Professor Herag assured his support in achieving our project's success.

Throughout the meeting, Professor Herag stressed the importance of adaptability and flexibility in shaping the project to meet our educational needs. In closing, he reiterated his commitment to supporting our learning experience and the project's success, recognizing our autonomy in decision-making.

# Project Charter

| General Project Information |  |  |  |
| --- | --- | --- | --- |
| Project Title | USC Housing Mobile Application - DormGrader | Executive Sponsor | University of Southern California |
| Project Start Date | November 6th, 2023 | Department Sponsor | Herag Haleblian |
| Project End Date | September 23rd, 2024 | Project Status | Project Plan Proposed |

| Project Team |  |
| --- | --- |
| Project Manager | Mihir Kavishwar |
| Project Team | Rhythm Deo |
|  | Sami Andari |
|  | Diya Shah |
|  | Gouzheng Yang |

Stakeholders

USC Board of Directors

USC Students and Staff

USC IT Department

Project Development Team

Marketing Team

Landlords in the Area

Advertised Businesses

Potential Investors or Funders

User Feedback Community

Competing Platforms

Regulatory Authorities

Campus Safety and Security

Business Justification

- USC students face ongoing housing challenges, including limited unbiased housing feedback and difficulties in finding compatible roommates and managing used items. - The project focuses on a mobile app to address these issues, with a key feature being genuine peer reviews to empower students and encourage better landlord practices. - The project's objectives are to save students time, enhance their housing experience, and address these challenges. - Specific objectives include improving housing searches with reliable reviews, roommate matching, and a used goods marketplace.

- The project also aims for financial self-sufficiency through integrated advertising.

Project Scope

In Scope

- Development of a mobile application for both iOS and Android platforms, encompassing three key sections: Housing Reviews, Roommate Matcher, and Buying/Selling Goods. - Creation of a web platform that is seamlessly compatible with the mobile application, ensuring a unified user experience. - Implementation of a secure student login system using USC ID, with automatic synchronization to streamline user registration and authentication. - Integration of an advertisement platform to generate revenue while maintaining user experience integrity. - Establishment of a direct communication channel via email for inquiries or user complaints. - Provision for users to include images when listing furniture for sale, enhancing the quality of listings. - Creation of generic user profiles for students to facilitate roommate matching, helping users find compatible living arrangements based on shared preferences and requirements. - Basic search and filtering options for users to find housing, roommates, and items for sale. - User notifications for key events, such as matches found or new listings. - User account management features for updating profiles and preferences. - Reporting functionality for inappropriate or fraudulent listings and users.

Out Scope

- Exclusion of features related to transportation, carpooling, or parking services, as these functionalities do not align with the application's core purpose. - No integration with institutions or systems outside of USC, as the application's primary focus is to serve the USC student community exclusively. - No incorporation of a chatbot system for handling complaints, as this is beyond the intended scope.

- Exemption from processing financial transactions within the application. - Omission of features unrelated to the main purpose, such as food delivery or ordering services. - Avoidance of becoming a full-fledged social media platform, keeping the primary focus on housing and roommate solutions. - No provision for hosting or managing non-furniture items for sale within the application. - Exclusion of responsibilities related to the creation of promotional or marketing materials for advertisers. - Non-engagement in handling non-academic or non-housing-related disputes, which are beyond the defined scope.

Project Success Criteria

- Design the application to accommodate future growth and a user base of at least 5,000 students within the first year. - Aim for an average user session duration of 5 minutes or more to encourage active user engagement. - Maintain a user retention rate of at least 60% after the first six months. - Target an average response time of less than 2 seconds for key interactions to ensure a responsive user experience. - Ensure compliance with data privacy regulations and conduct security audits for 100% data security. - Meet Web Content Accessibility Guidelines (WCAG) standards for inclusivity, especially for users with disabilities. - Implement marketing strategies to achieve a 5% increase in downloads and registrations every quarter during the first year. - Address technical issues within 24 hours and release regular updates every quarter to enhance user experience and security.

Project Deliverables

Initial Phase: - Develop a user-friendly mobile application for both iOS and Android platforms, featuring three key sections: Housing Reviews, Roommate Matcher, and Buying/Selling Goods, with a focus on intuitive cross-platform functionality.

- Create a seamlessly integrated web platform which ensures a unified user experience across devices. - Implement a secure USC ID-based login system for user convenience and data accuracy. - Strategically integrate an advertisement platform to generate revenue while preserving a smooth user experience. - Offer timely user notifications for matches and new listings, keeping users informed. - Provide a direct communication channel via email for inquiries and user support, ensuring timely issue resolution. Housing Reviews Section: - Maintain a robust rating system for accountability and the authenticity of reviews, prioritizing user trust. - Enable users to filter housing options based on location, price range, and amenities, tailoring their search. - Regularly update information and expand data on housing areas for accuracy. Roommate Matcher Section: - Create user profiles for students to share roommate preferences and expectations, enhancing compatibility. - Develop a matching mechanism to pair students with compatible profiles and encourage direct communication via USC email. - Implement user-friendly search and filtering options for easy discovery of housing, roommates, and items for sale. - Provide user account management features for profile customization and preferences. Buying/Selling Goods Section: - Enable users to post items for sale with images, descriptions, and prices, simplifying the listing process. - Facilitate the buying and selling of furniture among USC students, fostering a convenient marketplace within the university community. Security and Privacy:

- Ensure the security and confidentiality of user data through robust data protection and encryption techniques. - Strictly adhere to university data privacy policies, complying with regulatory standards. - Implement a secure login process for identity validation. - Develop reporting functionality for users to report inappropriate or fraudulent listings and users, maintaining platform integrity and safety.

Project Challenges

- Ensuring data security, especially for USC student IDs and personal information. - Efficiently managing server traffic during peak-demand periods for a responsive user experience. - Maintaining transparency and impartiality in housing reviews for accurate and trustworthy information. - Creating an inclusive, non-discriminatory environment for roommate matching, promoting a safe and respectful community. - Implementing strong measures to prevent online fraud and protect users in buying and selling goods. - Balancing revenue generation with user satisfaction for a sustainable income stream. - Regularly updating and upgrading data to accommodate new students every semester, ensuring accuracy and relevance.

Project Alternatives

- Create a web platform without a mobile application. - Develop a mobile application for either iOS or Android, instead of both platforms. - Explore partnerships with external institutions or systems beyond USC to enhance the application's functionality and user base. - Include the capability for users to process financial transactions within the application. - Expand the platform to include non-furniture items for sale. - Take on responsibilities for creating promotional and marketing materials for advertisers.

| Project Milestones |  |
| --- | --- |
| Project Initiation | December 5th, 2023 |
| Planning Phase | March 20th, 2024 |
| Development Phase | May 4th, 2024 |
| Testing Phase | July 24th, 2024 |
| Marketing and Roll Out Phase | August 30th, 2024 |
| Project Closure | September 23rd, 2024 |

Known Project Risks

- Data breaches due to security weaknesses or employee errors. - Biased housing reviews influenced by students or agents. - Low user adoption and acceptance of the software. - Privacy and security breaches, leading to unauthorized access or exposure. - Competition from other apps and options. - Technical challenges causing project delays. - Improper communication and misunderstandings within different teams. - Legal issues, including copyright infringement, data privacy breaches, and regulatory non- compliance. - Budget overruns, where the project budget exceeds projections. - Financial sustainability challenges, including insufficient revenue generation or market performance issues.

Project Constraint

- The project is constrained by a predetermined budget of approximately $800,000, which affects financial resource allocation. - Fixed start and end dates (November 6th, 2023, to September 23rd, 2024) impose schedule limitations.

- The project team is limited to assigned members, including the project manager and team, affecting resource availability. - Resource availability, particularly technology and development resources, is constrained. - User adoption expectations, like reaching a user base of 5,000 students, must be met for project success. - Adherence to data privacy regulations and 100% data security compliance is a binding constraint. - Technical issues must be resolved within a 24-hour timeframe. - Meeting marketing strategy targets for a 5% increase in downloads and registrations every quarter is essential for success.

Project Budget

Personnel: $250,000 - Salaries for project manager and team members. - Consultants or experts as needed. Technology and Development: $150,000 - Mobile application development for iOS and Android. - Web platform development. - Secure USC ID-based login system implementation. - Advertisement platform integration. User Notifications and Communication: $25,000 - Email communication channel setup. - User support and inquiry management. Housing Reviews Section: $75,000 - Rating system implementation. - Filter options for location, price range, and amenities. - Data updates and expansion. Roommate Matcher Section: $75,000 - User profiles creation. - Matching mechanism development. - Search and filtering options. - User account management features. Buying/Selling Goods Section: $25,000 - Item listing features. - Facilitating buying and selling of furniture.

Security and Privacy: $100,000 - Data security measures and encryption. - Compliance with data privacy policies. - Secure login process. - Reporting functionality. Marketing: $75,000 - Marketing strategies, campaigns, and user acquisition incentives. - Promotion of the application. - Monitoring user engagement. Legal and Compliance: $25,000 - Legal consultation for compliance. - Content moderation. - Terms of service establishment. Infrastructure and Maintenance: $20,000 - Server infrastructure and maintenance. Contingency: $5,000 - Reserved for unforeseen issues or additional requirements. Revised Total Budget: $800,000

| Project Sponsor Acceptance |  |  |  |
| --- | --- | --- | --- |
| Signature of Project Sponsor |  | Date |  |

# Work Breakdown Structure (WBS):

| Phase | Task Name | Description | Start | Finish | Critical path |
| --- | --- | --- | --- | --- | --- |
| Initiation | Define project objectives, scope, and requirements | Set the main objectives and boundaries | Mon 10/30/23 | Fri 11/10/23 | No |
| Initiation | Assemble project team | Formulate the necessary team | Mon 11/13/23 | Fri 11/24/23 | No |
| Initiation | Market Research | Understand market needs and competition | Mon 11/13/23 | Fri 11/17/23 | No |
| Initiation | Identify stakeholders | Recognize key parties involved in the project | Mon 11/13/23 | Fri 11/17/23 | No |
| Initiation | Develop the project charter | Draft a formal project directive | Mon 11/27/23 | Tue 12/5/23 | Yes |
| Planning | Develop a detailed project plan | Formulate a comprehensive plan | Wed 12/6/23 | Fri 4/5/24 | Yes |
| Planning | Create a project timeline | Schedule milestones and tasks | Fri 12/8/23 | Thu 12/14/23 | No |
| Planning | Allocate resources and budget | Assign resources and set budget | Fri 12/8/23 | Thu 12/21/23 | No |
| Planning | Finalize project scope | Confirm the boundaries and deliverables | Fri 12/22/23 | Thu 1/4/24 | No |
| Planning | Define technical requirements for the app | Specify tech needs and constraints | Fri 1/5/24 | Thu 1/11/24 | No |
| Planning | Research and select technology stack | Choose the appropriate tech tools | Fri 1/12/24 | Thu 1/25/24 | No |
| Planning | Design the user interface | Craft the UI for the app | Fri 1/26/24 | Thu 2/22/24 | No |
| Development | Begin app development | Start building the app | Fri 2/23/24 | Fri 2/23/24 | No |
| Development | Implement USC ID integration | Integrate university ID system | Mon 2/26/24 | Tue 3/5/24 | No |

| Development | Create the housing reviews, roommate matcher, buying/selling goods sections, and advertisement | Develop core features | Wed 3/6/24 | Tue 3/26/24 | No |
| --- | --- | --- | --- | --- | --- |
| Development | Conduct regular testing and debugging | Ensure app quality and functionality | Wed 3/27/24 | Tue 4/2/24 | No |
| Development | Content Writing | Generate content for the app | Wed 3/27/24 | Fri 4/5/24 | No |
| Development | Develop the web version alongside the mobile app | Parallel development of mobile and web versions | Wed 3/6/24 | Tue 3/19/24 | No |
| Development | Payment gateway integration | Enable financial transactions | Mon 2/26/24 | Mon 3/4/24 | No |
| Testing | Thoroughly test the application for functionality, security, and usability (Alpha test) | Comprehensive testing phase | Mon 4/8/24 | Fri 5/17/24 | No |
| Testing | Gather feedback from a pilot group of students (Beta testing) | Collect and analyze user feedback | Mon 5/20/24 | Fri 6/28/24 | Yes |
| Testing | Incorporate feedback and make necessary changes | Update the app based on user feedback | Mon 7/1/24 | Fri 7/26/24 | No |
| Testing | Final application testing | Perform a last round of comprehensive testing | Mon 7/29/24 | Fri 8/9/24 | No |
| Launch | Deploy app to production environment | Release the app to live environment | Mon 8/12/24 | Fri 8/16/24 | No |
| Launch | Launch promotion and marketing campaign | Advertise the app to target audience | Mon 8/19/24 | Fri 9/6/24 | Yes |

| Launch | User onboarding and training | Provide training and resources to new users | Mon 9/9/24 | Fri 9/20/24 | No |
| --- | --- | --- | --- | --- | --- |
| Post-launch | Collect user feedback post- launch | Gather insights and feedback post launch | Mon 9/23/24 | Fri 11/1/24 | No |
| Post-launch | Regular updates and maintenance | Ensure the app remains functional and up-to-date | Mon 11/4/24 | - | No |
| Post-launch | Monitor app performance and usage | Keep track of app metrics and user activity | Mon 11/4/24 | - | No |
| Maintenance | Evaluate user feedback | Analyze feedback for future improvements | Mon 11/4/24 | Fri 11/22/24 | No |
| Maintenance | Plan for next version | Strategize and plan features for next update/version | Mon 11/25/24 | Fri 12/20/24 | No |
| Maintenance | Security audit | Regular security checks to ensure data protection | Mon 1/6/25 | Fri 1/17/25 | Yes |
| Maintenance | Infrastructure scaling | Adjust server and infrastructure based on user load | Mon 1/20/25 | Fri 2/7/25 | No |
| Maintenance | Community engagement | Engage with users through forums, webinars, etc. | Mon 2/10/25 | - | No |
| Feedback | User surveys | Collect structured feedback through surveys | Mon 2/24/25 | Fri 3/7/25 | No |
| Feedback | Analyze survey results | Understand user sentiment and areas of improvement | Mon 3/10/25 | Fri 3/28/25 | No |

| Feedback | Implement changes | Make adjustments based on feedback | Mon 3/31/25 | Fri 4/25/25 | No |
| --- | --- | --- | --- | --- | --- |
| Testing Phase | Thoroughly test the application | Ensure functionality, security, and usability (Alpha test) | Mon 4/8/24 | Fri 5/17/24 | No |
| Testing Phase | Gather feedback from pilot group | Collect feedback from students (Beta testing) | Mon 5/20/24 | Fri 6/28/24 | Yes |
| Testing Phase | Performance test | Ensure the app performs well under load | Mon 4/8/24 | Fri 4/19/24 | No |
| Testing Phase | Make necessary revisions | Implement improvements based on tests | Mon 7/1/24 | Wed 7/24/24 | No |
| Rollout and Marketing Phase | Launch mobile and web version | Release the application to the public | Thu 7/25/24 | Thu 7/25/24 | Yes |
| Rollout and Marketing Phase | Promote the app to USC | Marketing and promotion activities | Fri 7/26/24 | Tue 8/6/24 | No |
| Rollout and Marketing Phase | User Feedback Collection | Collect feedback from the initial users for improvements | Wed 8/7/24 | Tue 8/20/24 | No |
| Rollout and Marketing Phase | App Updates | Implement feedback-based updates to the application | Wed 8/21/24 | Tue 9/10/24 | No |
| Rollout and Marketing Phase | Marketing Campaigns | Launch marketing campaigns to attract more users | Wed 9/11/24 | Thu 10/3/24 | No |

| Maintenance Phase | Routine Maintenance | Regular checks and updates for the application | From launch | Ongoing | No |
| --- | --- | --- | --- | --- | --- |
| Maintenance Phase | User Support | Provide support to the users facing any issues | From launch | Ongoing | No |
| Maintenance Phase | Periodic Updates | Release updates based on new features or improvements | Varies | Varies | Depends on update significance |
| Project Closure Phase | Evaluate the project's overall success | Determining how well the project met its objectives and overall goals | Mon 9/2/24 | Fri 9/6/24 | No |
| Project Closure Phase | Document lessons learned & Close Out Report, Impact Report | Compilation of experiences, learnings, and feedback for future reference | Mon 9/9/24 | Fri 9/20/24 | No |
| Project Closure Phase | Transition the project to an operational phase | Shifting the project from development to day-to-day operations | Mon 9/2/24 | Thu 9/12/24 | No |
| Project Closure Phase | Celebrate project completion | Commemorating the team's hard work and the project's success | Mon 9/23/24 | Mon 9/23/24 | No |

# Resource Plan:

| 1. Personnel |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sr. no | Role | Description | Quantity | Duration |
| 1.1 | Project Manager | Oversees the project, ensuring it stays on schedule, budget, and meets the project objectives | 1 | Full project duration |
| 1.1.1 | PM Team | Assists the PM | 1 | Full project duration |
| 1.2 | UI/UX Designers | Design the user interface and user experience for the mobile and web platforms. | 2 | Up to Design completion |
| 1.3 | Backend Developer | Handles server-side logic, database management, and API development. | 2 | Up to Deployment |
| 1.4 | Frontend Developer | Develops the user interface for both mobile apps and the web platform | 2 | Up to Deployment |
| 1.5 | QA Tester | Ensures the product is bug-free by conducting various tests | 1 | Development completion to Deployment |
| 1.6 | Support team | Handles user registration, data management, and user support | 1 | After Project Deployment |
| 1.7 | Marketing Personnel | Handles promotion, advertisement, and outreach for the app. | 2 | From Development to completion life cycle of the app |
| 1.8 | Content Moderator | To ensure unbiased and appropriate content, content moderators will review and approve reviews, listings, and user-generated content. | 1 | From Development completion to life cycle of the app |

| 1.9 | Financial Analysts | Experts in finance will monitor income sources, such as advertisements, to ensure the application's financial self-sufficiency. | 1 | Development completion to Deployment |
| --- | --- | --- | --- | --- |
| 1.1 | Legal advisors | Legal experts will ensure compliance with relevant regulations and privacy standards. | 1 | From development to deployment |
| 1.11 | Customer Support | Customer support representatives will address user inquiries and issues. | 2 | From Development completion to life cycle of the app |
| 2. Tools and Technologies |  |  |  |  |
| Sr No. | Tools | Description | Options | Duration |
| 2.1 | Software | Software licenses for development (IDEs, design tools, database management, etc.) |  | Continuous, with provisions for scaling |
| 2.2 | Server Hosting | Cloud hosting for backend, database, and potentially the web platform. | AWS, Google Cloud, Azure | Continuous, with provisions for scaling |
| 2.3 | Testing Tools | Software tools to aid in unit, integration, and user acceptance testing. | Licenses based on the number of testers | Continuous, with provisions for scaling |
| 3. Miscellaneous |  |  |  |  |
| Sr no | Tools | Description | Quantity | Duration |
| 3.1 | Marketing Materials | Graphics, promotional video | As needed based on the marketing strategy | As needed based on the marketing strategy |
| 3.2 | Feedback Platforms | Platforms or tools to gather user feedback during beta testing. | 1 platform licenses based on the number of users | As per the need of the team |

| 3.3 | Ad Platform | To integrate advertisements for revenue. | 1 platform, with considerations for reach and relevance | As A17:E40per the need of the team |
| --- | --- | --- | --- | --- |

# Project Organization:

The organizational chart you've described seems to be designed to facilitate the efficient development and management of the mobile application, web platform, and related services for the University of Southern California (USC) project. Let's break down the reasons for this specific organizational structure based on the project's scope:

- University of Southern California (USC): USC is at the top of the organizational chart because they are the project's client and ultimate authority. Professor Haleblian may represent the client's interests and vision for the project.

- Project Manager: The project manager is crucial for overseeing the entire project, ensuring that it aligns with USC's goals, is completed within the specified time and budget, and that all components work together cohesively.

- PM Teams (1) and (2): The division into two project management teams might be due to the complexity of the project. Each team can focus on specific aspects of the project (e.g., mobile app and web platform), making management more efficient.

ISE 515: Project Management (Team 4)

- Legal Advisors: Legal advisors are essential to ensure that the project complies with relevant laws and regulations, protecting both the project and USC.

- Frontend and Backend Developers: These teams are responsible for building the mobile application and web platform, respectively. Separating them can streamline development and ensure that each aspect is optimized for its specific platform.

- UI/UX Design: Placing the UI/UX Design under the Frontend Developer ensures a smooth collaboration between design and development teams, which is crucial for creating an attractive and user-friendly application.

- Content Moderator: This role is responsible for ensuring that user-generated content, like housing reviews and classified ads, meets USC's content guidelines.

- Financial Analysts: Financial analysts can help with revenue generation through advertisements and financial planning for the project.

- Marketing Personnel: They play a key role in promoting the application and web platform, attracting users, and generating revenue.

- QA Tester: QA testers ensure the quality and functionality of the application and web platform.

- Customer Support: Placing Customer Support under the Content Moderator suggests that they may work closely to address user inquiries and complaints related to content.

- Support Team: The support team is positioned under the Backend Developer, as they are responsible for maintaining and troubleshooting the backend infrastructure.

The organizational chart seems designed to promote efficient communication and collaboration among different teams and roles, helping to ensure the successful development and operation of the mobile application, web platform, and related services according to USC's specific requirements and the project's scope. The project manager's role is central in coordinating all these teams to achieve the project's goal.

- Project Schedule: LINK FOR MPP: Final project schedule.mpp

### Critical Path:

# Risk Plan:

Risk Probability and Impact

| IMPACTS |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | 0 - Acceptable | 1- Tolerable | 2- Unacceptable | 3- Intolerable |
| LOW - Risk unlikely to occur | Low | Low-Med | Low-Med | Medium |
| MEDIUM - Risk will likely occur | Low | Low-Med | Medium | High |
| HIGH - Risk will occur | Low- Med | Medium | Medium | High |

| Risk name | Description | Likelihood | Impact | Mitigation | Contingency |
| --- | --- | --- | --- | --- | --- |
| Data Breach | Data breaches can result from intentional exploitation of security weaknesses or accidental exposure of sensitive data, either through malicious actions or employee errors. | Medium | 3 | Employ high- security measures and regular audits. | In response to a data breach, contain, investigate, notify, restore, enhance security, and communicate effectively. |
| Biased Housing Reviews | Some students can be biased or influenced by the agents to submit dishonest reviews | High | 2 | Implement review verification systems and moderation. | Block the user after few warnings |

| User Adoption | Users might not accept the software. | Medium | 2 | Launch a comprehensive marketing campaign to attract users, offer incentives for early adoption, and continually improve the app's user experience to increase engagement. | Change management encompasses user involvement in design and development, ongoing monitoring and feedback, and offering incentives for adoption. |
| --- | --- | --- | --- | --- | --- |
| Privacy and Security | Privacy and security breaches happen when sensitive information or systems are accessed or exposed without authorization. | High | 3 | Implement robust data encryption, enforce strict data access controls, conduct regular security audits, and stay up-to- date with data protection laws. | Identify, contain, notify, investigate, mitigate, communicate, recover, and learn from the incident to minimize harm and prevent future breaches. |
| Competitive Landscape | There can be enough other apps and options | Medium | 3 | Conduct a thorough market analysis to identify unique selling points, continuously innovate to stay ahead of competitors, and build a strong brand and community. | Real-time competitor analysis, adaptive tactics, innovation, and risk assessment to navigate competitive dynamics and seize opportunities uniquely. |

| Technical Challenges | The intricacy of the project's technical aspects could potentially lead to a postponement | Medium | 2 | Employ a dedicated technical team, conduct stress testing, and invest in reliable server infrastructure to minimize technical issues. Implement regular software updates and bug fixes. | Create transparent and well-defined technical requirements, such as operating systems, platforms, and cloud services, and appoint competent individuals to manage technical problems. |
| --- | --- | --- | --- | --- | --- |
| Improper Communication | Misunderstanding and lack of effective communication can take place in different teams | Medium | 1 | Make certain that the project team possesses the essential skills and knowledge required to tackle technical difficulties. | Establishing transparent communication standards for all parties involved, including team members, clients, and external vendors. |
| Legal and Compliance | Copyright infringement, data privacy breaches, contract disputes, and regulatory non-compliance | High | 3 | Consult legal experts to ensure compliance with data protection regulations, implement content moderation to prevent legal issues, and establish clear terms of service for users. | Adhering to all applicable laws, regulations, and best practices, seeking legal counsel when needed, and implementing thorough compliance processes from the start. |

| Budget Overruns | Project budget runs out or less revenue generation than projected | Medium | 2 | Continuously monitor expenditures and put into action a strategy for cost reduction. | Create an exhaustive budget encompassing all anticipated costs, such as personnel salaries, software licenses, hardware, and any other project- related expenses. |
| --- | --- | --- | --- | --- | --- |
| Financial Sustainability | No regular generation of revenues or app doesn't do well in the market | Medium | 2 | Diversify revenue streams, secure venture capital or funding sources, and maintain a lean operation to extend financial runway and ensure long- term sustainability. | Target new customer segments or geographic markets to increase your customer base. License or franchise your software to third parties for a fee. |